## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start Date | Due Date | Late | Completed Date | Completed By | Description | Completed Checklist Items | Checklist Items | Labels
1 | Create initial prototype illustrating one key concept from the project. | Client presentation | Completed | Medium | (s) Harry Parker;(s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Thomas Philpott | 02/12/2021 |  | 12/01/2022 | false | 13/01/2022 | (s) James Rudd
2 | Create communication plan. | Client presentation | Completed | Medium | (s) James Rudd;(s) Thomas Philpott | (s) Thomas Philpott | 02/12/2021 |  | 12/01/2022 | false | 13/01/2022 | (s) James Rudd
3 | Create risk management plan. | Client presentation | Completed | Medium | (s) Thomas Philpott | (s) Thomas Philpott | 02/12/2021 |  | 12/01/2022 | false | 13/01/2022 | (s) Thomas Philpott
4 | Create initial interface diagrams (sitemap, wireframes etc) | Client presentation | Completed | Medium | (s) Harry Parker;(s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Thomas Philpott | 02/12/2021 |  | 12/01/2022 | false | 06/01/2022 | (s) Harry Parker
5 | Create set of requirement models. (Create user stories, use case diagrams and other appropriate UML diagrams that decompose the user stories) | Client presentation | Completed | Medium | (s) Oliver Donnellan;(s) Thomas Philpott | (s) Thomas Philpott | 02/12/2021 |  | 12/01/2022 | false | 06/01/2022 | (s) Harry Parker
6 | Create sprint plan showing when user stories will be developed by the team and an outline of what will be released at the end of each sprint. | Client presentation | Completed | Medium | (s) Harry Parker | (s) Thomas Philpott | 02/12/2021 |  | 12/01/2022 | false | 03/01/2022 | (s) Harry Parker
7 | Create main project objectives. | Client presentation | Completed | Medium |  | (s) Thomas Philpott | 02/12/2021 |  | 12/01/2022 | false | 30/12/2021 | (s) Thomas Philpott
8 | Discuss what language/framework will be used | Sprint 1 - 8/12/21 - 22/12/21 | Completed | Medium | (s) Harry Parker;(s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Thomas Philpott | 28/11/2021 |  |  | false | 03/01/2022 | (s) Harry Parker
9 | Discuss and make sure that requirements are clear | Sprint 1 - 8/12/21 - 22/12/21 | Completed | Medium |  | (s) Thomas Philpott | 28/11/2021 |  |  | false | 30/12/2021 | (s) Thomas Philpott
10 | Initial Client Meeting | Sprint 1 - 8/12/21 - 22/12/21 | Completed | Medium |  | (s) Harry Parker | 22/12/2021 |  |  | false | 30/12/2021 | (s) Thomas Philpott
11 | Backend tasks - views, triggers and tables | Sprint 10 - 13/04/22 - 27/04/22 | Not started | Medium | (s) James Rudd | (s) James Rudd | 29/04/2022 |  | 03/05/2022 | true
11 | Implement CMS | Sprint 11 - 27/04/22 - 11/05/22 | Completed | Important | (s) Harry Parker;(s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Thomas Philpott | 12/05/2022 |  | 12/05/2022 | false | 12/05/2022 | (s) Harry Parker |  | 2/2 | Setup Textpattern;Convert HTML pages to CMS pages
12 | Final Showcase Presentation | Sprint 12 - 11/05/22 - 25/05/22 | Not started | Medium | (s) Harry Parker;(s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Harry Parker | 14/03/2022 |  | 17/05/2022 | false
13 | Team Poster | Sprint 12 - 11/05/22 - 25/05/22 | Completed | Medium |  | (s) Harry Parker | 12/05/2022 |  | 16/05/2022 | false | 12/05/2022 | (s) Harry Parker
14 | Individual Report | Sprint 12 - 11/05/22 - 25/05/22 | Completed | Medium | (s) Harry Parker;(s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Harry Parker | 14/03/2022 |  | 09/05/2022 | false | 12/05/2022 | (s) Harry Parker
15 | Final demonstration to client | Sprint 12 - 11/05/22 - 25/05/22 | Completed | Medium | (s) Harry Parker;(s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Harry Parker | 14/03/2022 |  | 11/05/2022 | false | 12/05/2022 | (s) Harry Parker
16 | UI design for any extra features (e.g. IP/Email blocking) | Sprint 2 - 22/12/21 - 5/01/22 | Completed | Medium | (s) Harry Parker;(s) Oliver Donnellan | (s) Thomas Philpott | 28/11/2021 |  |  | false | 12/05/2022 | (s) Harry Parker
17 | Learn basics of drupal | Sprint 2 - 22/12/21 - 5/01/22 | Completed | Medium | (s) Harry Parker;(s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Thomas Philpott | 22/12/2021 |  | 05/01/2022 | false | 14/03/2022 | (s) Harry Parker
18 | UI design - Planning News | Sprint 2 - 22/12/21 - 5/01/22 | Completed | Medium | (s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Thomas Philpott | 30/12/2021 |  | 05/01/2022 | false | 13/01/2022 | (s) Thomas Philpott
19 | UI design - Trees | Sprint 2 - 22/12/21 - 5/01/22 | Completed | Medium | (s) Harry Parker | (s) Thomas Philpott | 30/12/2021 |  | 05/01/2022 | false | 07/01/2022 | (s) Harry Parker
20 | Search function mockup design | Sprint 2 - 22/12/21 - 5/01/22 | Completed | Medium |  | (s) Thomas Philpott | 28/11/2021 |  | 05/01/2022 | false | 07/01/2022 | (s) Harry Parker
21 | UI design - Our Landscapes | Sprint 2 - 22/12/21 - 5/01/22 | Completed | Medium |  | (s) Thomas Philpott | 30/12/2021 |  | 05/01/2022 | false | 03/01/2022 | (s) Harry Parker
22 | UI design - Contact Members | Sprint 2 - 22/12/21 - 5/01/22 | Completed | Medium |  | (s) Thomas Philpott | 28/11/2021 |  | 05/01/2022 | false | 03/01/2022 | (s) Harry Parker
23 | UI design - Admin page | Sprint 2 - 22/12/21 - 5/01/22 | Completed | Medium |  | (s) Thomas Philpott | 28/11/2021 |  | 05/01/2022 | false | 03/01/2022 | (s) Harry Parker
24 | UI design - Events | Sprint 2 - 22/12/21 - 5/01/22 | Completed | Medium | (s) Harry Parker | (s) Thomas Philpott | 30/12/2021 |  | 05/01/2022 | false | 02/01/2022 | (s) Harry Parker
25 | UI design - Membership Form | Sprint 2 - 22/12/21 - 5/01/22 | Completed | Medium |  | (s) Thomas Philpott | 28/11/2021 |  | 05/01/2022 | false | 02/01/2022 | (s) Harry Parker
26 | UI design - News section (main dashboard?) | Sprint 2 - 22/12/21 - 5/01/22 | Completed | Medium |  | (s) Thomas Philpott | 28/11/2021 |  | 05/01/2022 | false | 02/01/2022 | (s) Harry Parker
27 | UI design - About Us section | Sprint 2 - 22/12/21 - 5/01/22 | Completed | Medium |  | (s) Thomas Philpott | 28/11/2021 |  | 05/01/2022 | false | 02/01/2022 | (s) Harry Parker
28 | Write project vision. | Sprint 2 - 22/12/21 - 5/01/22 | Completed | Medium | (s) Thomas Philpott | (s) Thomas Philpott | 02/12/2021 | 22/12/2021 | 12/01/2022 | false | 30/12/2021 | (s) Thomas Philpott
29 | Create basic dashboard prototype | Sprint 3 - 5/01/22 - 19/01/22 | Completed | Medium | (s) Harry Parker;(s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Thomas Philpott | 28/11/2021 |  | 18/01/2022 | false | 20/01/2022 | (s) Harry Parker | Has to include one key concept: Membership Form and maybe drupal integration?
30 | Marketplace Demo Video Review | Sprint 3 - 5/01/22 - 19/01/22 | Completed | Medium | (s) Harry Parker;(s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Harry Parker | 03/01/2022 |  | 19/01/2022 | false | 20/01/2022 | (s) Harry Parker
31 | Marketplace Demo (zoom call) | Sprint 3 - 5/01/22 - 19/01/22 | Completed | Medium | (s) Harry Parker;(s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Harry Parker | 03/01/2022 | 18/01/2022 | 18/01/2022 | false | 18/01/2022 | (s) James Rudd | Time: 9:30
32 | Interim Document (Individual) | Sprint 3 - 5/01/22 - 19/01/22 | Completed | Medium | (s) Harry Parker;(s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Harry Parker | 02/01/2022 |  | 14/01/2022 | false | 15/01/2022 | (s) Thomas Philpott
33 | Client Presentation Powerpoint | Sprint 3 - 5/01/22 - 19/01/22 | Completed | Medium | (s) Harry Parker;(s) Oliver Donnellan;(s) James Rudd;(s) Thomas Philpott | (s) Thomas Philpott | 22/12/2021 |  | 01/12/2022 | false | 14/01/2022 | (s) Harry Parker | Have a PowerPoint presentation showcasing our objectives, requirement models, user stories, case diagrams, and UML diagrams.
34 | Create Our Landscapes page for demo | Sprint 3 - 5/01/22 - 19/01/22 | Completed | Medium | (s) Oliver Donnellan | (s) Thomas Philpott | 06/01/2022 |  |  | false | 13/01/2022 | (s) Harry Parker
35 | Create Home page for demo | Sprint 3 - 5/01/22 - 19/01/22 | Completed | Medium | (s) Thomas Philpott | (s) Thomas Philpott | 06/01/2022 |  |  | false | 13/01/2022 | (s) Thomas Philpott
36 | Create About page for demo | Sprint 3 - 5/01/22 - 19/01/22 | Completed | Medium | (s) James Rudd | (s) Thomas Philpott | 06/01/2022 |  |  | false | 10/01/2022 | (s) James Rudd
37 | Create Membership Form page for demo | Sprint 3 - 5/01/22 - 19/01/22 | Completed | Medium | (s) Harry Parker | (s) Thomas Philpott | 06/01/2022 |  |  | false | 08/01/2022 | (s) Harry Parker
38 | Feedback Receiving? | Sprint 4 - 19/01/22 - 2/02/22 | Completed | Medium |  | (s) Harry Parker | 14/03/2022 |  | 15/02/2022 | false | 14/03/2022 | (s) Harry Parker
39 | Feedback Receiving? | Sprint 5 - 2/02/22 - 16/02/22 | Completed | Medium |  | (s) Harry Parker | 14/03/2022 |  | 15/02/2022 | false | 14/03/2022 | (s) Harry Parker
40 | Apply Demo Feedback | Sprint 6 - 16/02/22 - 02/03/22 | Completed | Medium |  | (s) Harry Parker | 14/03/2022 |  | 02/03/2022 | false | 14/03/2022 | (s) Harry Parker
41 | Text tranches part 1 written up | Sprint 6 - 16/02/22 - 02/03/22 | Completed | Medium |  | (s) Harry Parker | 14/03/2022 |  | 27/02/2022 | false | 14/03/2022 | (s) Harry Parker
42 | Second text tranche | Sprint 7 - 02/03/22 - 16/03/22 | Completed | Medium | (s) Thomas Philpott | (s) Harry Parker | 14/03/2022 |  | 21/03/2022 | false | 09/05/2022 | (s) Thomas Philpott |  | 7/7 | Why Trees Matter page;Protecting Trees page;Trees & Hedgerows page;South Devon AONB page;Planning Campaigning page;Planning Object page;Our Woodlands page
43 | Importing project into drupal | Sprint 7 - 02/03/22 - 16/03/22 | Completed | Medium | (s) Oliver Donnellan | (s) Harry Parker | 14/03/2022 |  | 21/03/2022 | false | 24/03/2022 | (s) Harry Parker
44 | Third text tranche | Sprint 7 - 02/03/22 - 16/03/22 | Completed | Medium | (s) Harry Parker | (s) Harry Parker | 14/03/2022 |  | 16/03/2022 | false | 24/03/2022 | (s) Harry Parker |  | 4/4 | Devon's Landscapes page;Our Economy page;Coast & Estuaries page;What We Are Doing page
45 | First text tranche | Sprint 7 - 02/03/22 - 16/03/22 | Completed | Medium |  | (s) Harry Parker | 14/03/2022 |  | 21/03/2022 | false | 24/03/2022 | (s) Harry Parker |  | 5/5 | Planning Process page;About us page;Planning Introduction page;Home page;Our Landscape page

## Plan name
Plan name | Group B Backlog
Plan ID | h5sVXiUYLUq-6ZmVql00uZYABS89
Date of export | 13/05/2022