## Sheet1
RAID Category | Type of RAID Category | Description | Impact | Priority | Status | Actions to take | Group B
Risk | Technical | Injection | Unauthorised view of back-end data | Moderate | Open | Ensure that login/register input data is passed in safely. | Risk Management Plan
Issue | Technical | Membership form not submitting | User cannot apply for membership | Critical | Open | Make sure the form is submitted correctly through the website
Risk | Technical | Members and Adminstrators having weak passwords | There is a higher risk of malicious threats succesfully bruteforcing passwords | Critical | Open | Require adminstrator and member passwords to contain uppercase characters, numbers, and special characters.
Risk | Team | Lack of communication between team members | Confusion caused within the team environment | Low | N/A | Daily messages to ensure everything's ok. Team meetings are scheduled at a mininum every 2 weeks
Risk | Knowledge | Lack of specialist knowledge in using Drupal CMS | Unsuccessful Integration | Moderate | Open | This can be recitified by essential reading and additional research
Issue | Technical | Membership details not saved in database | Lost of personal data | Critical | Open | This can be corrected by making sure that the database is connected to the website in a way that the membership details are saved correctly
Issue | Technical | Website format incorrect on other devices | Website usability is low | Critical | Open | Making sure that the code ensures that the layout of the website is what is expected to be on any device including mobile phones
Risk | Team | Team Member not participating in the group project as intended | Total productivity and work done is decreased | Low | N/A | We ensure that each member is participating in the project fully else there would be actions taken against the member